## Sheet1
Staff |  |  |  | Stages
| Planning (9 days) | Analysis (80 days) | Designing (25 days) | Developing (40 days) | Testing (12 days) | Deploy (7 days) | Maintain (10 days) | Total Time
Project Manager (Jericho Marvin Ramit) | 3 hours * 9 days | 2 hours * 80 days | 1 hour * 40 days | 1 hour * 40 days | 1 hour * 12 days | 1 hour * 7 days | 1 hour * 10 days | 281 hours
Graphic Desiger (Jericho Marvin Ramit/ Kathleen Seagan) |  |  | 3 hours * 25 days |  | 1 hour * 12 days | 2 hours * 7 days | 2 hours * 10 days | 121 hours
System Programmer (Mark Ferdinand Almuete/ Kathleen Seagan) | 3 hours * 9 days | 6 hours * 80 days |  | 8 hours * 40 days | 6 hours * 12 days | 4 hours * 7 days | 4 hours * 10 days | 967 hours
Writer Editor (Rollie Altea) |  | 4 hours * 9 days |  | 2 hours * 40 days | 2 hours * 12 days | 3 hours * 7 days | 3 hours * 10 days | 191 hours
Quality Assurance (Rollie Altea/ Jericho Marvin Ramit) |  | 4 hours * 80 days |  | 2 hours * 40 days | 3 hours * 12 days | 2 hours * 7 days | 2 hours * 10 days | 470 hours
Total Time | 54 hours | 996 hours | 100 hours | 520 hours | 156 hours | 84 hours | 120 hours | 2030 hours